## Verification Checklist
ID | Section | Requirement Statement | Type | Priority | Verification Methods (from SRS) | Primary Method (select) | Acceptance Criteria | Agent Procedure (step-by-step) | Evidence to Collect | Owner/Role | Phase/Gate | Status | Date Last Updated | Test Case ID / Link | Upstream Trace | Downstream Trace | Notes
TRW-001 | 9.1 Workflow Triggering & Scope | The workflow **shall run only** in response to a `workflow_run` of the upstream workflow named **“CI Pipeline (Composite)”**. | Functional | High | Inspection, Demonstration | Inspection | Only `workflow_run` is declared with `workflows: [CI Pipeline (Composite)]` and `types: [completed]`. | Open `.github/workflows/draft-release.yml`. Verify `on.workflow_run.workflows` includes `CI Pipeline (Composite)` and `on.workflow_run.types` includes `completed`. Confirm no other event triggers (`push`, `pull_request`, schedule) are defined for this workflow. | Workflow YAML snippet showing the `on: workflow_run` section.; Screenshot or log of event payload proving trigger source. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 109; Verified .github/workflows/draft-release.yml allows only workflow_run from CI Pipeline (Composite) with type completed; no other triggers.
TRW-002 | 9.1 Workflow Triggering & Scope | The workflow **shall proceed only** when the upstream `workflow_run.conclusion` equals `success`. | Functional | High | Test | Test | Workflow runs when `conclusion=success` and does not run (or exits early) when `conclusion≠success`. | Create a controlled upstream run with `conclusion=success` and another with `conclusion=failure` (e.g., dispatch or replay). Observe draft-release workflow behavior for both upstream runs. | Two run URLs with conclusions and downstream run status.; Logs showing conditional gate `github.event.workflow_run.conclusion == 'success'`. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 110; Guard present in .github/workflows/draft-release.yml to exit unless workflow_run.conclusion == success.
TRW-003 | 9.1 Workflow Triggering & Scope | The workflow **shall proceed only** when the upstream workflow was triggered by a `push` event. | Functional | High | Test | Test | Downstream workflow proceeds only when upstream `event` is `push`; other events are skipped. | Ensure the job has an early `if:` guard: `github.event.workflow_run.event == 'push'`. Trigger an upstream run caused by `push` and one by `pull_request`; observe behavior. | YAML snippet with `if: ${{ github.event.workflow_run.event == 'push' }}`.; Run logs/screens showing skip on non-push events. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 111; Guard present in .github/workflows/draft-release.yml to exit unless workflow_run.event == push.
TRW-004 | 9.1 Workflow Triggering & Scope | The workflow **shall evaluate the upstream `head_branch`** against a configurable allow‑list of patterns: `main`, `develop`, `release-alpha/*`, `release-beta/*`, `release-rc/*` (default), with support for extension via configuration. | Functional | High | Analysis/Simulation, Test | Analysis/Simulation | Branches in allow-list proceed; others are blocked with a clear diagnostic. | Identify the allow-list patterns (e.g., `main`, `develop`, `release-*`). Verify gate logic evaluates `github.event.workflow_run.head_branch` against the list. Test with branches matching and not matching the list. | Config file or YAML `if` expression showing pattern check.; Run logs from both allowed and disallowed branches. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 112; Allow-list enforced in .github/workflows/draft-release.yml with defaults (main, develop, release-alpha/*, release-beta/*, release-rc/*) and optional extensions via ALLOWED_BRANCH_PATTERNS.
TRW-005 | 9.1 Workflow Triggering & Scope | For branches outside the allow‑list, the workflow **shall terminate** with a **no‑op outcome** and perform **no tag or release operations**. | Functional | High | Test | Test | No tags or releases created; logs indicate no-op by branch policy. | Execute a run from a branch not in the allow-list. Confirm the workflow exits with a no-op and performs no tag or release operations. | Run log capturing no-op decision.; Release/tags UI showing no changes. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 113; Branch allow-list gate in .github/workflows/draft-release.yml exits before tag/release steps for disallowed branches.
TRW-006 | 9.1 Workflow Triggering & Scope | The workflow **shall define a concurrency group** that ensures only one run per commit SHA is active at a time; subsequent runs for the same SHA **shall cancel** or **queue** per configuration. | Process/Quality | High | Inspection, Demonstration | Inspection | At most one active run per commit; either queued or cancelled per configuration. | Open workflow YAML and locate `concurrency:`. Verify `group` includes the commit SHA (e.g., `${{ github.sha }}`) and `cancel-in-progress: true` (or per policy). Trigger two runs for the same commit and observe deduping/queuing. | YAML snippet of `concurrency` block.; Run timeline screenshots showing queuing/cancellation. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 114; Concurrency configured in .github/workflows/draft-release.yml with group: ${{ github.workflow }}-${{ github.event.workflow_run.head_sha }} and cancel-in-progress: true to ensure one run per commit.
TRW-010 | 9.2 Versioning & Bump Logic | The workflow **shall compute the next version** from: (a) last reachable tag; (b) parsed semantic version; and (c) commit count since that tag as **BUILD**. | Functional | High | Analysis/Simulation, Test | Analysis/Simulation | Version is computed from last tag, parsed semver, and commit count as build number. | Fetch full git history (`fetch-depth: 0`). Resolve last reachable tag and parse semantic version; determine commit count since tag. Compute next version candidate. | Logs with last tag, parsed parts, and commit count.; Printed `VERSION_STRING`. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 120; Compute-version action derives MAJOR/MINOR/PATCH from last reachable tag, defaults to 0.1.0 if none, and sets BUILD to commit count since that tag.
TRW-011 | 9.2 Versioning & Bump Logic | When no previous tag exists, the base version **shall default to `0.1.0`** prior to applying bump rules. | Functional | Medium | Test | Test | When no prior tag exists, version defaults to configured base (e.g., `0.1.0`). | Delete tags locally/in test repo to simulate no previous tag. Run version computation routine. | Log excerpt showing base version fallback path.; `VERSION_STRING` value in output. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 121; Compute-version action falls back to base version 0.1.0 when no prior tag exists before applying bump rules.
TRW-012 | 9.2 Versioning & Bump Logic | In **PR CI context**, the bump type **shall be determined by PR labels**: `major`, `minor`, or `patch`; exactly one such label shall be present; if none, **default to `patch`**; if multiple, **fail** the computation with a clear diagnostic. | Functional | High | Test | Test | Bump type follows labels; multiple label case fails; none defaults to `patch`. | Create a PR with label `major`, then with `minor`, then with `patch`. Create a PR with multiple bump labels to observe failure. Create a PR with no bump labels to observe default. | CI logs mapping label to bump type.; Failure log for multiple labels. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 122; Compute-version action selects bump from PR labels (major/minor/patch), defaults to patch when none, and fails with a clear diagnostic if multiple labels are present.
TRW-013 | 9.2 Versioning & Bump Logic | In **push context on release branches**, the default bump type **shall be at least `patch`** unless overridden by explicit configuration. | Functional | High | Test | Test | Push on release branches yields at least a `patch` bump by default. | Push commits to a release branch (e.g., `release-alpha/x`). Observe default bump type selection (≥ patch) unless overridden in config. | Logs showing selected bump type and branch context. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 123; Compute-version action defaults bump to patch on release branches (release-alpha/*, release-beta/*, release-rc/*, release/*) in non-PR contexts.
TRW-014 | 9.2 Versioning & Bump Logic | The workflow **shall emit outputs**: `MAJOR`, `MINOR`, `PATCH`, `BUILD_NUMBER`, `VERSION_STRING`, and `IS_PRERELEASE`. | Interface | High | Test | Test | `MAJOR`, `MINOR`, `PATCH`, `BUILD_NUMBER`, `VERSION_STRING`, and `IS_PRERELEASE` are exported and visible to subsequent steps. | Run the version step and capture exported outputs. | Job output or `GITHUB_OUTPUT` file contents. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 124; Compute-version action exports MAJOR, MINOR, PATCH, BUILD_NUMBER, VERSION_STRING, and IS_PRERELEASE for downstream steps.
TRW-015 | 9.2 Versioning & Bump Logic | Pre‑release suffix rules **shall** be applied by branch: `release-alpha/*` → `alpha.<BUILD>`; `release-beta/*` → `beta.<BUILD>`; `release-rc/*` → `rc.<BUILD>`; other allowed stable branches → **no suffix**. | Functional | High | Test | Test | Suffixes match `alpha.<BUILD>`, `beta.<BUILD>`, `rc.<BUILD>`; stable has none. | Execute the workflow on `release-alpha/*`, `release-beta/*`, and `release-rc/*` branches and on a stable branch. Verify suffix formation per branch and that stable branches have no suffix. | Computed version strings for each branch case. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 125; Compute-version action applies suffixes alpha.<BUILD>, beta.<BUILD>, rc.<BUILD> for release-alpha/beta/rc branches and no suffix for stable branches.
TRW-016 | 9.2 Versioning & Bump Logic | Stable branches **shall** produce versions **without** any pre‑release suffix; pre‑release branches **shall** include the configured suffix. | Functional | High | Test | Test | Stable branches produce suffix-free versions; prerelease branches include suffix. | Trigger runs on stable vs prerelease branches. Confirm that only prerelease branches append a suffix. | Logs showing `IS_PRERELEASE` and final version strings. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 126; Compute-version action marks prerelease branches with suffix and sets IS_PRERELEASE=true; stable branches emit no suffix and IS_PRERELEASE=false.
TRW-020 | 9.3 Tag Naming & Uniqueness | The tag name format **shall be** `v<MAJOR>.<MINOR>.<PATCH>.<BUILD>`. | Interface | High | Inspection, Test | Inspection | Tag string matches exact pattern `vX.Y.Z.N`. | Confirm tag format logic produces `v<MAJOR>.<MINOR>.<PATCH>.<BUILD>` (with optional suffix in version, not in tag). Generate example tags from computed version. | Printed tag value; regex check result. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 132; draft-release workflow forms tags as v<MAJOR>.<MINOR>.<PATCH>.<BUILD> without prerelease suffix.
TRW-021 | 9.3 Tag Naming & Uniqueness | Before creating a tag, the workflow **shall check** for an existing tag with the same name and, if present, **shall retrieve its target SHA**. | Functional | High | Test | Test | If tag exists, corresponding object SHA is retrieved. | Query repository for tag existence (via `git ls-remote --tags` or API). Capture SHA if present. | Command output or API response showing tag and SHA. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 133; draft-release workflow checks origin for existing tag and captures SHA via git ls-remote before creation.
TRW-022 | 9.3 Tag Naming & Uniqueness | If the tag exists and **resolves to the same commit** SHA as the current run, the workflow **shall treat the condition as success** and **shall not** create a duplicate tag; release creation may be skipped per configuration. | Functional | High | Test | Test | Existing tag on same commit is treated as success; no duplicate operations performed. | Create a tag on the same commit and rerun workflow. Observe that run treats it as success and optionally skips release creation per config. | Logs indicating detection of same-commit tag and skip path. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 134; draft-release workflow treats existing tag on same commit as success and skips duplicate creation.
TRW-023 | 9.3 Tag Naming & Uniqueness | If the tag exists and **resolves to a different commit**, the workflow **shall fail** with a clear conflict diagnostic and **shall not** move or overwrite the tag. | Functional | High | Test | Test | Workflow fails with explicit diagnostic; tag is not moved or overwritten. | Create a tag with the same name but pointing to a different commit. Run the workflow and observe failure and no overwrite. | Logs with the two SHAs and failure status.; Tag ref still points to original commit. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 135; draft-release workflow fails if existing tag points to a different commit and does not overwrite it.
TRW-024 | 9.3 Tag Naming & Uniqueness | The workflow **shall prevent** different branches from generating identical tags by incorporating BUILD and (where applicable) pre‑release suffix rules in §9.2. | Quality/Design Constraint | High | Analysis/Simulation, Test | Analysis/Simulation | Different branches do not produce identical tags; collision path is blocked. | Run two branches that could compute the same version (e.g., ensure build numbers or suffixes disambiguate). Verify the workflow prevents identical tag generation across branches. | Logs showing branch-safe versioning decision. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 136; draft-release workflow fails on conflicting existing tags, ensuring different branches cannot produce identical tags and overwrite each other.
TRW-030 | 9.4 Artifact Requirements & Validation | The workflow **shall rely on artifacts** uploaded by the upstream CI run associated with the triggering `workflow_run`. | Functional | High | Demonstration | Demonstration | Workflow downloads artifacts from upstream run. | Verify presence of artifact download step referencing the upstream `workflow_run` ID. | Logs of artifact download with run ID. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 142; draft-release workflow downloads artifacts from the triggering workflow_run via actions/download-artifact using run-id.
TRW-031 | 9.4 Artifact Requirements & Validation | The workflow **shall download** the artifacts of the triggering `workflow_run`. | Functional | High | Test | Test | Artifacts are retrieved to the runner workspace. | Enumerate artifacts available from `workflow_run` and download them. | Artifact list and local file tree snapshot. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 143; draft-release workflow downloads artifacts from triggering workflow_run and lists them under artifacts/ for verification.
TRW-032 | 9.4 Artifact Requirements & Validation | The workflow **shall locate exactly one** `.vip` package and **exactly one** release notes Markdown file within the downloaded artifacts. | Functional | High | Test | Test | Exactly one of each required artifact is located. | Search the artifacts for exactly one `.vip` package and exactly one release-notes markdown file. | File list with counts; names of selected files. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 144; draft-release workflow enforces exactly one .vip and one release_notes_*.md in artifacts, failing on missing or plural occurrences.
TRW-033 | 9.4 Artifact Requirements & Validation | The filenames of those artifacts **shall contain** the computed `VERSION_STRING` to enforce **version–artifact consistency**. | Quality | High | Test | Test | Both filenames contain the computed version string. | Compare computed `VERSION_STRING` against artifact filenames. | Screenshot or log of filename match check. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 145; draft-release workflow validates both artifact filenames contain computed version string.
TRW-034 | 9.4 Artifact Requirements & Validation | If any required artifact is missing or pluralized, the workflow **shall fail** with an actionable diagnostic. | Functional | High | Test | Test | Workflow fails when artifacts are missing/duplicated, with specific error code/message. | Simulate missing or pluralized artifacts by removing or duplicating files. Run the workflow to observe failure with actionable diagnostics. | Failure logs including diagnostic details. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 146; Locate-artifacts step fails with detailed counts and file list when required artifacts are missing or duplicated.
TRW-040 | 9.5 Release Creation & Publishing | The workflow **shall create a draft GitHub Release** and attach the `.vip` and release notes assets. | Functional | High | Test | Test | Draft release exists with both `.vip` and release notes attached. | Call the Releases API (or use action) to create a draft release with assets. | Release page URL and asset list. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 152; draft-release workflow uses softprops/action-gh-release to create a draft release with .vip and release notes attached.
TRW-041 | 9.5 Release Creation & Publishing | The GitHub Release **shall set** the **prerelease flag** according to `IS_PRERELEASE`. | Interface | High | Test | Test | Release `prerelease` flag matches computed `IS_PRERELEASE`. | Ensure `prerelease` flag in release object follows `IS_PRERELEASE`. Verify both true and false cases. | API response or UI screenshot for both cases. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 153; Releases created/updated with prerelease flag set from IS_PRERELEASE output.
TRW-042 | 9.5 Release Creation & Publishing | When a release with the computed tag already exists, the workflow **shall update** that release record rather than create a new one. | Functional | Medium | Test | Test | Existing release is updated in place; no duplicate release is created. | If a release with the computed tag exists, update it rather than creating a new one. | Release history showing updates, not new creation. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 154; Publish step reuses existing release if present, otherwise creates and updates the same release record (no duplicates).
TRW-043 | 9.5 Release Creation & Publishing | Upon successful validation, the workflow **shall publish** the release (transition from draft) and **shall mark it as latest** per repository policy. | Functional | High | Test | Test | Release is published and marked latest (if applicable). | Transition a draft to published and set as latest per repo policy. | Release status in UI/API. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 155; draft-release publish step updates existing release, sets draft=false, make_latest=true, and respects prerelease flag.
TRW-044 | 9.5 Release Creation & Publishing | All operations **shall authenticate** using `GITHUB_TOKEN` with `contents: write`. | Interface/Security | High | Inspection, Test | Inspection | `GITHUB_TOKEN` scopes allow required operations. | Confirm `GITHUB_TOKEN` permissions include `contents: write`. Attempt an operation requiring those permissions and confirm success. | Permission settings and successful API call logs. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 156; Workflow/job permissions grant contents: write and all release/tag operations use GITHUB_TOKEN.
TRW-050 | 9.6 Error Handling, Retries & Robustness | Tag push operations **shall be retried** (minimum 3 attempts, ≥5s back‑off between attempts). | Quality/Reliability | Medium | Test | Test | Tag push is retried (e.g., 3 attempts, 5s delay) before final failure/success. | Attempt to push tag with a simulated transient error and verify retry mechanism (e.g., mock failure or use retryable command). | Logs showing retry count and delays. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 162; Tag creation step retries push 3 times with 5s backoff before failing.
TRW-051 | 9.6 Error Handling, Retries & Robustness | Release API operations **shall detect** a not‑found (404) response and **shall create** the release; other API errors **shall be handled gracefully** with diagnostics and non‑destructive behavior. | Quality/Reliability | High | Test | Test | 404 triggers creation path; other errors are surfaced with graceful handling. | Invoke release API to fetch by tag; if 404, create release; handle other codes per policy. | Logs for 404 branch and for non-404 error handling. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 163; Publish step handles 404 by creating release and surfaces other errors gracefully (no destructive actions).
TRW-052 | 9.6 Error Handling, Retries & Robustness | The workflow **shall be non‑destructive** with respect to existing tags; it **shall never move** an existing tag ref. | Quality/Safety | High | Inspection, Test | Inspection | Existing tags are never moved automatically. | Create an existing tag and attempt to move it; verify the workflow refuses to force-update. | Git command logs; tag ref remains unchanged. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 164; draft-release workflow refuses to move existing tags (fails on conflict, never force-updates).
TRW-053 | 9.6 Error Handling, Retries & Robustness | Re‑runs of the workflow for the same commit and computed version **shall be idempotent**, producing no duplicate tags or releases and no conflicting state. | Quality | High | Test | Test | No duplicate tags/releases are created on re-runs; operations are idempotent. | Re-run the workflow for the same commit and inputs twice. | Run history and resulting refs/releases (no duplicates). | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 165; draft-release workflow skips existing same-commit tags and upserts releases, preventing duplicates on reruns.
TRW-060 | 9.7 Observability & Logging | The workflow **shall log** at start: commit SHA, head branch, upstream `workflow_run` ID, computed `VERSION_STRING`. | Process/Usability | Medium | Inspection, Demonstration | Inspection | All required context fields are logged in a structured way. | Check logs include commit SHA, branch, workflow_run ID, and version string. | Log excerpts with the four fields present. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 171; draft-release logs commit, branch, workflow_run ID, and version via context logging step.
TRW-061 | 9.7 Observability & Logging | The workflow **shall log** decision outcomes: bump type, suffix rule applied, tag existence outcome, artifact discovery results. | Process/Usability | Medium | Inspection, Demonstration | Inspection | Each decision point emits a structured log entry. | Confirm decision logs for bump, suffix rules, tag existence, and artifact discovery. | Collected log entries covering all decision items. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 172; Workflow logs bump type, suffix application, tag existence outcome, and artifact discovery decisions.
TRW-062 | 9.7 Observability & Logging | All failure conditions **shall include** actionable diagnostics indicating detection point, probable cause, and remediation guidance. | Process/Quality | High | Inspection | Inspection | Failures include actionable diagnostics (errors, causes, next steps). | Induce a few failure modes and check that detailed diagnostics are emitted. | Failure logs for representative cases. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 173; Failure paths emit actionable diagnostics with detection point, cause, and remediation (tag conflicts, push retries, artifact validation).
TRW-070 | 9.8 Efficiency & Runner Behavior | The workflow **shall perform a single repository checkout** per job. | Process/Efficiency | Medium | Inspection | Inspection | Only one checkout step is present. | Ensure repository uses a single `actions/checkout` per job. | Workflow YAML highlighting checkout usage. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 179; draft-release job performs a single actions/checkout step.
TRW-071 | 9.8 Efficiency & Runner Behavior | The workflow **shall ensure full Git history** is available for tag reachability and commit counting. | Process/Correctness | High | Inspection, Test | Inspection | Full git history is available to the job. | Verify `fetch-depth: 0` or equivalent full-history fetch is configured. | Checkout step config and `git rev-list` depth proof. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 180; draft-release checkout uses fetch-depth: 0 for full history to support reachability and commit counting.
TRW-072 | 9.8 Efficiency & Runner Behavior | The workflow **shall not leave persistent configuration side effects** on self‑hosted runners (no global git config mutations beyond the job scope). | Process/Safety | High | Inspection | Inspection | Runner state is clean post-run (no orphaned files/tokens/config). | Run on a self-hosted runner and verify no persistent configuration side effects remain after completion. | Before/after runner state diff, cleanup logs. | Automation QA (Agent) | CI Integration | Completed | 2025-11-20 |  |  |  | Derived from SRS line 181; Workflow uses local git config only; no global/persistent state changes on runners.